## Sheet1
Track | Category | Risk Reference | Risk Title | Description and Impact | Risk Response | Status | Owner | RAG Status
Program Management | Common | R1 | Detailed Scope Unknown | Functional Scope and User stories are currently in evolving stage. The project timeline and budget is fixed. Post scope clarity, there might be a situation where scope may not exactly fit into available timelines. | 1) Functional Requirements, User stories need to be available at the earliest. 2) MVP definitions to consider available capacity and timelines for each journey and prioritize accordingly. | Not occurred
DevOps | Common | R2 | CI/CD Pipeline Implementation | Journey garages and CI/CD implementation has kicked off in parallel. VM Allocations, access provisions and other internal processes have SLAs, PO for licenses are in progress as CI/CD implementation works in parallel. Entire CI/CD pipeline may not be ready before 10th of July. | 1) Share comprehensive VM requirements in advance. 2) Expedite internal approvals 3) Expedite PO for licenses | Not occurred
Resourcing | Internal | R3 | Resource onboarding | Project has aggressive timelines. Engineering needs to start by 15th July. Resources with niche skills will need to be ramped up in shorter time frame that is available. | 1) Internal functions to search for the resources available on bench 2) IN case the external recruitment is needed, requirements need to be floated immediately. | Not occurred
Infrastructure | Common | R4 | Infrastructure setup | VMWare requirements are getting finalised. By 15th of July, infrastructure needs to be available with setup. At current pace, procurement and licencing may not complete in time for 15th July start. | 1) POs with VMWare, AWS (as appropriate) need to be expedited. | Not occurred
Technical | Common | R5 | Interface Details | Identification of target state system in scope that our microservices may need to integrate with and interface specifications for them | 1) Identification of target state systems in scope. Publish interface specs. | In Analysis
Data Security | Common | R6 | NSE Security Standards | Publish PII handling rules, Encryption requirements for data, audit requirements | 1) requirements for data security, encryption needs and standards | Not occurred
Technical | Common | R7 | App and Data overlap among different journeys | Application function or data captured/synthesized can be same in multiple reimagination journeys leading to increase in effort and operations | 1) Requirement of Application & Data Governance reporting to Program Governance for any duplication of work | Not occurred
Technical | Common | R8 | Common Framework Components and Customization | Preparation of all common framework components/business functions may not be possible to envisag before development start leading to change in approach & increase in effort | 1) Common horizontal framework utilities needs to be designed and developed first and then vertical /journey wise functions | Not occurred
| Common | R9 | Addition of new tools in implementation | Addition of any new tools needs to be envisaged and selected before implementation start. Otherwise it can create changes in implementation | 1) Addition of new tools/ softwares should be complete for all 3rd party vendors before implementation | Not occurred
| Common | R10 | Phase wise launch approach | Phase wise production launch with old and new systems simultaneously running can lead to conflict or data duplicacy | 1) Migration or Launch approach needs to be discussed with its phase wise impact analysis needs to be designed and documented in detail | Not occurred
DevOps | Common | R11 | DB related tools imlementation | DB setup of tools like Liquibase and Oracle Enterprise Manager | 1) DBA to Manage the versions of the DB schema for Liquibase 2)DBA to setup and integration tasks for OEM | Not occurred
Data Security | Common | R6 | NSE Security Standards | Publish PII handling rules, Encryption requirements for data, audit requirements | 1) requirements for data security, encryption needs and standards | Not occurred
Technical | Common | R7 | Test environment - up to date | Test environment should be have latest codebase version. | 1) Test environment update with latest version | In Analysis
Product Backlog | Common | R8 | Release Backlog is unavailable for the planned MVP in ALM tool | There are chances missing the release/MVP goals and will impact on the overall project schedules. | 1) Release backlog updates in the JIRA. 2) MVP/Release planning to walk through the overall MVP objectives with Garage teams. | In Progress
Agile Practices | Common | R9 | The delay in agreement on agile trainings, practices like sprint cadence, built-in-quality, governance and metrics across teams to follow unified pocess | Team alignment, program execution and quality related issues that impact overall project goals | 1) Walk through the agreed Agile practices across Garage teams 2) Agile traninings across teams to be completed before start of the sprint execution | In Progress