## Sheet1
Security team had raised following queries in various discussion. However, they have not been answered to their satisfaction. | Assigned To | Date of Submission | Status
1. Data flow of Leased Line traffic to the Google Cloud deployed Apigee solution. | Raja Sekhar | 2020-05-08 | Submited
Implemented the Flow diagram for NSE Staff
2. Security design of 2 factor authentication. - Anand Nevrekar | Anand Nevrekar | 2020-11-08 | Inprogress
Authenticate user - open for discussion
3. API & OAuth security design documents on Apigee. | Raja Sekhar | 2020-11-08 | Submited
Implemented the Flow diagram
4. Hardening documents for all the components proposed to be deployed.
5. All web application & mobile apps for Static content | Raja sekhar |  | Submited

## Sheet2
S.No. | Method | user story | Service Name | Description | Endpoint
1 | POST | Managing segments accessible to different users | UserService | Post the data in segementBundleMapping table | /v1/segmentBundleMapping
Request
Object |  |  | Example
segmentRequestList |  | Array | { "segmentRequestList":[ { "userId":"UserMapping10", "segmentName":"Segment Sprint 4", "isOperationFlag" :true },{ "userId":"UserMapping10", "segmentName":"Segment Sprint 2", "isOperationFlag" :true } ] }
Object
| userId | String(50), Required
| segmentName | String(50), Required
| isOperationFlag | Boolean[true,false], Required
Response
Error Details